## text
II. Detailed Budget Form | [8 empty] | Currency: USD
Activity | time line | No. | 1. EXPENDITURE | 1. EXPENDITURE |  |  |  | 2. INCOME
|  |  | person | Budget category | Budget Item | Breakdown | Amount | Applicant | Other funding source | Japan Foundation | Breakdown
Preparatory Phase (January- March 1999)
Preparation of pilot web site incorporating basic materials on CSW | Jan – Feb |  | JCA
Consultation on AWORC database indexing strategy to enhance accessibility to BPFA related resources | Jan – Feb |  | JCA APWIN
Collection and integration of index information to AWORC database | Jan–Mar+ (ongoing) |  | JCA
Travel arrangements and logistics for May training workshop | Mar |  | JCA
Participation in the CSW Beijing Review Process Deliberations: | Mar 2nd, 3rd Wk |  | Isis SAATHI
* Presentation of the web site and promotion of AWORC to attract more participants and obtain feedback during the CSW meeting | "" |  | Isis SAATHI
* Survey to evaluate capacity of women's organizations to utilize information technology and available information on the AWORC website | "" |  | Isis SAATHI |  |  | - | - |  | IDRC being consulted | -
Reporting of the Five Year Review Process through the website in English and several Asian languages | Mar-May |  | Isis SAATHI
Fiscal Year 1 (April 1999- March 2000)
Preparation of draft training module and training materials | Apr | 1 | JCA APWIN | honoraria | Training module preparation | $1000*1 [contract] = $1000 | 1000 |  | 978.5714 | 21.4286 | $1000*1 [contract]
|  | 2 |  | printing | Draft Training material (in print) | $10*10sets = $100 | 100 |  | 100 | 0 | $10*10sets
Half-yearly Website evaluation, also based on feedback from CSW | Apr | 3 | JCA all | report preparation | website evaluation report | cost to be covered under salary for assistant coordinator | 0 |  |  | 0 | cost to be covered under salary for assistant coordinator
Trainers training and finalization of training of the training course and materials with core member organization (Manila, Philippines) | Apr | 4 | JCA APWIN all | int'l travel | international travel to Manila | $750( economy average from Asia)*5persons = $3750 | 3750 |  | 610 | 3140 | $750( economy average from Asia)*5persons
|  | 5 |  | printing | Training material (in print) | $10*50sets = $500 | 500 |  |  | 500 | $10*50sets
|  | 6 |  | local transport | local transport (AirPort-Isis) | $12*5*2ways(Airport-Isis) = $120 | 120 |  | 120 | 0 | $12*5*2ways(Airport-Isis)
|  | 7 |  | boarding | boarding (Isis) | $10*5nights*5persons = $250 | 250 |  | 250 | 0 | $10*5nights*5persons
|  | 8 |  | expenses | food | $150/day*5day = $750 | 750 |  | 750 | 0 | $150/day*5day
|  | 9 |  | facilities | Training facilities | $32*5days = $160 | 160 |  | 160 | 0 | $32*5days
|  | 10 |  | honoraria | trainer per diem | $30*5days = $150 | 150 |  | 150 | 0 | $30*5days
|  | 11 |  | communications | trainee followup consulting (phone) | $20/m*9m = $180 | 180 |  |  | 180 | $20/m*9m
Incorporation of the online feedback mechanism for promotion and evaluation of the web site | May | 12 | JCA Isis | honoraria | web design | $50*5days = $250 | 250 |  | 250 | 0 | $50*5days
|  | 13 |  | salary | Training module web version | $50*4days = $200 | 200 |  | 200 | 0 | $50*4days
Hiring of co-coordinators and assistants [Philippines,Japan] | Jun | 14 | JCA Isis | salary | co-coordinator[Isis] | $250(2wk/m)*12m [philippins] = $3000 | 3000 |  |  | 3000 | $250(2wk/m)*12m [philippins]
|  | 15 |  | salary | co-coordinator[JCA-NET] | $500(1wk/m)*12m [japan] = $6000 | 6000 |  |  | 6000 | $500(1wk/m)*12m [japan]
|  | 16 |  | salary | technical assistants [JCA-NET] | $100/day*5days*12m[japan] = $6000 | 6000 |  |  | 6000 | $100/day*5days*12m[japan]
|  | 17 |  | communications | Int'l phone calls for coordination | $25/m*12m = $300 | 300 |  |  | 300 | $25/m*12m
5 days training workshop with the participating organization on Internet usage and web site development for Beijing Review: | Jun | 18 | JCA APWIN all | int'l travel | international travel to Seoul [including 2 trainers] | $750(average)*15persons from Asia = $11250 | 11250 |  | 5000 | 6250 | $750(average)*15persons from Asia
|  | 19 |  | printing | Training material | $5*30 = $150 | 150 |  |  | 150 | $5*30
|  | 20 |  | local transport | local transport | $100*6days = $600 | 600 |  |  | 600 | $100*6days
|  | 21 |  | boarding | boarding | $50/day*7days*20persons = $7000 | 7000 |  | 7000 | 0 | $50/day*7days*20persons
|  | 22 |  | facilities | Training facilities | $1000*5days = $5000 | 5000 |  | 5000 | 0 | $1000*5days
|  | 23 |  | honoraria | trainer honoraria | $30*5days*2persons = $300 | 300 |  | 300 | 0 | $30*5days*2persons
|  | 24 |  | honoraria | Training module web version | $100*1 = $100 | 100 |  | 100 | 0 | $100*1
|  | 25 |  | communications | trainee followup consulting (phone) | $20/m*9m = $180 | 180 |  |  | 180 | $20/m*9m
Monthly updating of the web site with information on activities and events; reports and analyses of NGOs, government bodies and international agencies; information about organizations and networks involved in the Beijing Review process | Aug–Mar+ (onging) | 26 | JCA Isis APWIN All | communications | cmmunications support cost | $200*15groups = $3000 | 3000 |  |  | 3000 | $200*15groups
II. Detailed Budget Form (continued)
Activity | time line | No. | 1. EXPENDITURE | 1. EXPENDITURE |  |  |  | 2. INCOME
|  |  | person | Budget category | Budget Item | Breakdown | Amount | Applicant | Other funding source | Japan Foundation | Breakdown
Half-yearly Website evaluation | Oct | 27 | JCA all | report preparation | website evaluation report | cost to be covered under salary for assistant coordinator | 0 |  |  | 0 | cost to be covered under salary for assistant coordinator
2000
Compilation of activity report for distribution (mail &at CSW) | Feb | 28 | All | communications | postage | $3(average)*50 = $150 | 150 |  |  | 150 | $3(average)*50
|  | 29 |  | supplies | diskett,explanation,packaging | $3*50sets = $150 | 150 |  |  | 150 | $3*50sets
Participation in the CSW Meeting: | Mar 2nd, 3rd Wk | 30 | Isis SAATHI | int'l travel | international travel to Cnference Site | $1000*1person = $1000 | 1000 |  |  | 1000 | $1000*1person
|  | 31 |  | boarding | boarding | $75*1person*10days = $750 | 750 |  |  | 750 | $75*1person*10days
* Presentation of web site report to Asian Caucus; and | "" | 32 | Isis SAATHI |  |  |  | 0 |  |  | 0
* online reporting of Caucus and CSW activities for the web site | "" | 33 | Isis SAATHI | communications | communications cost | $20day*10 = $200 | 200 |  |  | 200 | $20day*10
|  | 34 |  | salary | reporting staff cost | $50*10days*1person = $500 | 500 |  |  | 500 | $50*10days*1person
* Survey to evaluate capacity of women's organizations to utilize information technology and available information on the AWORC website | "" | 35 | Isis SAATHI |  |  | - | - |  | IDRC being consulted | -
Travel arrangements and logistics for May training workshop | Mar | 36 | Isis SAATHI |  |  |  | 0 |  |  | 0
|  |  |  | TOTAL (for year 1) |  |  | 53040 | 0 | 20968.5714 | 32071.4286 | total for yr 1
Activity | time line | No. | 1. EXPENDITURE | 1. EXPENDITURE |  |  |  | 2. INCOME
|  |  | person | Budget category | Budget Item | Breakdown | Amount | Applicant | Other funding source | Japan Foundation | Breakdown
Fiscal Year 2 (April 2000- March 2001)
Hiring of co-coordinators and assistant [Philippines,Japan] | Apr | 37 | JCA Isis | salary | co-coordinator[Isis] | z = $3000 | 3000 |  |  | 3000 | z
|  | 38 |  | salary | co-coordinator[JCA-NET] | $500(1wk/m)*12m [japan] = $6000 | 6000 |  |  | 6000 | $500(1wk/m)*12m [japan]
|  | 39 |  | salary | technical assistants [JCA-NET] | $100/day*5days*12m[japan] = $6000 | 6000 |  |  | 6000 | $100/day*5days*12m[japan]
|  | 40 |  | communications | Int'l phone calls for coordination | $25/m*12m = $300 | 300 |  |  | 300 | $25/m*12m
Monthly updating of the web site with information on activities and events; reports and analyses of NGOs, government bodies and international agencies; information about organizations and networks involved in the Beijing Review process | Apr–Mar+ (onging) | 41 | JCA Isis APWIN All | communications | cmmunications support cost | $200*15groups = $3000 | 3000 |  |  | 3000 | $200*15groups
Half-yearly Website evaluation, also based on feedback from CSW | Apr | 42 | JCA all | report preparation | website evaluation report | cost to be covered under salary for assistant coordinator | 0 |  |  | 0 | cost to be covered under salary for assistant coordinator
II. Detailed Budget Form (continued)
Activity | time line | No. | 1. EXPENDITURE | 1. EXPENDITURE |  |  |  | 2. INCOME
|  |  | person | Budget category | Budget Item | Breakdown | Amount | Applicant | Other funding source | Japan Foundation | Breakdown
5 days training workshop with the participating organization on Internet usage and web site development for Beijing Review: | May | 43 | JCA Isis APWIN | int'l travel | international travel to Seoul [including 2 trainers] | $750(average)*15persons from Asia = $11250 | 11250 |  | other sponsers being consulted | 11250 | $750(average)*15persons from Asia
|  | 44 |  | printing | Training material | $5*30pieces = $150 | 150 |  |  | 150 | $5*30pieces
|  | 45 |  | local transport | local transport | $100*6days = $600 | 600 |  |  | 600 | $100*6days
|  | 46 |  | boarding | boarding | $50/day*7days*20persons = $7000 | 7000 |  | 7000 | 0 | $50/day*7days*20persons
|  | 47 |  | facilities | Training facilities | $1000*5days = $5000 | 5000 |  | 5000 | 0 | $1000*5days
|  | 48 |  | honoraria | trainer | $100*5days = $500 | 500 |  | 500 | 0 | $100*5days
|  | 49 |  | honoraria | Training module web version | $100*1 = $100 | 100 |  | 100 | 0 | $100*1
Participation during the UN Beijing Plus Five Conference | Jun | 50 | Isis SAATHI | int'l travel | international travel to Conference Site | $1000*2persons = $2000 | 2000 |  | 714.2857 | 1285.7143 | $1000*2persons
|  | 51 |  | boarding | boarding/expenses | $75*2person*10days = $1500 | 1500 |  |  | 1500 | $75*2person*10days
* Provide online reporting of Caucus and Conference activities for the web site | "" | 52 | Isis SAATHI | communications | communications cost for reporting | $20day*10 = $200 | 200 |  |  | 200 | $20day*10
|  | 53 |  | salary | reporting staff cost | $50*10days*1person = $500 | 500 |  |  | 500 | $50*10days*1person
Participation in the Review of Section J (Media - including Information technology) | "" | 54 | Isis SAATHI |  |  |  | - |  | IDRC being consulted | -
Compilation of activity report for distribution (mail &at CSW) | Jul | 55 |  | communications | postage | $3(average)*50sets = $150 | 150 |  |  | 150 | $3(average)*50sets
|  | 56 |  | supplies | diskett,explanation,packaging | $3*50sets = $150 | 150 |  |  | 150 | $3*50sets
Half-yearly Website evaluation | Oct | 57 | JCA all | report preparation | website evaluation report | cost to be covered under salary for assistant coordinator | 0 |  |  | 0 | cost to be covered under salary for assistant coordinator
2001
Compilation of project activity report, including post-Conference materials prepared by women's gorups and distribution | Dec | 58 | JCA Isis APWIN All | Reporting | Final evaluation report drafting | $100*3days = $300 | 300 |  |  | 300 | $100*3days
Coordinator meeting to evaluate Beijing Review project and finalize activity report | Jan | 59 | JCA Isis APWIN SAAHTI | int'l travel | international travel to Seoul | $750(average)*5persons = $3750 | 3750 |  | 3750 | 0 | $750(average)*5persons
|  | 60 |  | local transport | local transport | $16(Airport)*5person*2trip = $240 | 240 |  | 240 | 0 | $16(Airport)*5person*2trip
|  | 61 |  | boarding | boarding | $75/day*3days*5persons = $1125 | 1125 |  | 1125 | 0 | $75/day*3days*5persons
Distribution of activity report to participating organizations and at CSW meeting | Mar | 62 |  | communications | postage | $3(average)*50 = $150 | 150 |  |  | 150 | $3(average)*50
|  | 63 |  | supplies | diskett,explanation,packaging | $3*50sets = $150 | 150 |  |  | 150 | $3*50sets
|  |  |  | TOTAL (for year 2) |  |  | 53115 | 0 | 18429.2857 | 34685.7143 | total for yr 2
|  |  |  | TOTAL (for 2year program) |  |  | 106155 | 0 | 39397.8571 | 66757.1429 | total for full duration (2yr)

## worksheet
II. Detailed Budget Form | [8 empty] | Currency: USD
Activity | time line | No. | 1. EXPENDITURE | 1. EXPENDITURE |  |  |  | 2. INCOME
|  |  | person | Budget category | Budget Item | Breakdown | Amount | Applicant | Other funding source | Japan Foundation
Fiscal Year 1 (April 1999- March 2000)
Preparation of draft training module and training materials | Apr | 1 | JCA APWIN | honoraria | Training module preparation | = $1000 | 1000 |  | 978.5714 | 21.4286
|  | 2 |  | printing | Draft Training material (in print) | = $100 | 100 |  | 100 | 0
Half-yearly Website evaluation, also based on feedback from CSW | Apr | 3 | JCA all | report preparation | website evaluation report |  | 0 |  |  | 0
Trainers training and finalization of training of the training course and materials with core member organization (Manila, Philippines) | Apr | 4 | JCA APWIN all | int'l travel | international travel to Manila | = $3750 | 3750 |  | 610 | 3140
|  | 5 |  | printing | Training material (in print) | = $500 | 500 |  |  | 500
|  | 6 |  | local transport | local transport (AirPort-Isis) | = $120 | 120 |  | 120 | 0
|  | 7 |  | boarding | boarding (Isis) | = $250 | 250 |  | 250 | 0
|  | 8 |  | expenses | food | = $750 | 750 |  | 750 | 0
|  | 9 |  | facilities | Training facilities | = $160 | 160 |  | 160 | 0
|  | 10 |  | honoraria | trainer per diem | = $150 | 150 |  | 150 | 0
|  | 11 |  | communications | trainee followup consulting (phone) | = $180 | 180 |  |  | 180
Incorporation of the online feedback mechanism for promotion and evaluation of the web site | May | 12 | JCA Isis | honoraria | web design | = $250 | 250 |  | 250 | 0
|  | 13 |  | salary | Training module web version | = $200 | 200 |  | 200 | 0
Hiring of co-coordinators and assistants [Philippines,Japan] | Jun | 14 | JCA Isis | salary | co-coordinator[Isis] | = $3000 | 3000 |  |  | 3000
|  | 15 |  | salary | co-coordinator[JCA-NET] | = $6000 | 6000 |  |  | 6000
|  | 16 |  | salary | technical assistants [JCA-NET] | = $6000 | 6000 |  |  | 6000
|  | 17 |  | communications | Int'l phone calls for coordination | = $300 | 300 |  |  | 300
5 days training workshop with the participating organization on Internet usage and web site development for Beijing Review: | Jun | 18 | JCA APWIN all | int'l travel | international travel to Seoul [including 2 trainers] | = $11250 | 11250 |  | 5000 | 6250
|  | 19 |  | printing | Training material | = $150 | 150 |  |  | 150
|  | 20 |  | local transport | local transport | = $600 | 600 |  |  | 600
|  | 21 |  | boarding | boarding | = $7000 | 7000 |  | 7000 | 0
|  | 22 |  | facilities | Training facilities | = $5000 | 5000 |  | 5000 | 0
|  | 23 |  | honoraria | trainer honoraria | = $300 | 300 |  | 300 | 0
|  | 24 |  | honoraria | Training module web version | = $100 | 100 |  | 100 | 0
|  | 25 |  | communications | trainee followup consulting (phone) | = $180 | 180 |  |  | 180
Monthly updating of the web site with information on activities and events; reports and analyses of NGOs, government bodies and international agencies; information about organizations and networks involved in the Beijing Review process | Aug–Mar+ (onging) | 26 | JCA Isis APWIN All | communications | cmmunications support cost | = $3000 | 3000 |  |  | 3000